**WASEC**

**PROJECT WASEC Deliverable**

**Minutes of the 2nd Bi-monthly Skype Meeting**

**10.06.2019**

|  |  |
| --- | --- |
| **Project acronym:** | WaSec |
| **Project full title:**  | Innovations in Water Education Programs: Enhancing Water Security and Socio-economic Development in the Eastern Mediterranean under Climate Change / WaSec |
| **Grant agreement no.:** | 598480-EPP-1-2018-1-​PS-EPPKA2-CBHE-JP (2018-3826) |
| **Responsible partner for deliverable:** | PTUK |
| **Contributing partners:** | PTUK, EMATTECH |
| **Author(s):** | S. Khayat, George Zaimes |
| **Dissemination level[[1]](#footnote-1):** | CO |
| **Total number of pages:** | 6 |
| **Version:**  | 1.0 |
| **Delivery date:** | 10/06/2019 |

Version control

|  |  |  |
| --- | --- | --- |
| Number | Date | Description |
| 1 | 10-06-2019 | First draft sent to the George Zaimes (Saed Khayat) |
| 2 | 12-06-2019 | Second Draft with revision by George Zaimes |
| 3 | 13-06-2019 | Third Draft corrected by Nawaf Abu-Khalaf |

1. **Date: 10.06.2019**
2. **Beginning Time: 11:00 EET**
3. **Ending Time: 11:35 EET**
4. **Participants:**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Name** | **Institute** | **Notes** |
| 1 | Saed Khayat | PTUK | Project Coordinator |
| 2 | George Zaimes | EMATTECH | Greece |
| 3 | Amer Marei | AQU | Palestine |
| 4 | Ruba Hassan | JUST | Jordan |
| 5 | Thanasis Hadzilacos | OUC | Cyprus |
| 6 | Leena Mrashdeh | UJ | Jordan |
| 7 | Jawad Al-Bakri | UJ | Jordan |
| 8 | Josel Gracia | UPM | Spain |
| 9 | Martin Gimenez | UPM | Spain |
| 10 | Ben Sonneveld | VU/Amesterdam | Nederland |
| 11 | Muath Abu Sada | Hydo/pal | Palestine |
| 12 | Nawaf Abu- Khalaf | PTUK | Palestine |
| 13 | Othman Mashaqbeh | PSUT | Jordan |
| 14 | Maya Dimitriadou | CreThiDEv | Greece |
| 15 | Vassilis Liskas  | OUC | Cyprus |

1. **Meeting Themes to be discussed**
* Progress of WP.1.1 and 1.2.
* Dissemination plan and project website
* Master Program, new courses and Courses development
* Next preventive meeting in 2nd of July with Palestine NLO
* Next Meeting in Kavala/Greece
* External Advisory committee
1. **Proceeding**

In context of the WaSec project activities, the second bi-monthly meeting has been conducted through a skype group call, where the following discussion has been exchanged between participants, and moderated by George Zaimes (EMaTTech).

1. The WP. 1.1 has been discussed in detail because of the upcoming deadlines in regard to its deliverables. Emphasis was given to the surveying process and number of surveys needed from each partner. Statistical information and the current status from the University of Jordan were given. The process of filling enterprises-Universities relation surveys which may be switched with personal interview in some cases still need more participants. All partners were urged to contact the necessary target groups in order to have the necessary feedback .
2. Thanasis (OUC) explained the draft for the concept of W.P. 2.2.1. The final draft will be sent to all partners after the meeting to approve the final version, and after many notes and amendments have been done according to scientific committee comments that has been received earlier.
3. Ruba (JUST explained the progress of dissemination, the website which currently has some problem due to internal server errors. All partners have sent the necessary information for the project website. She also requested a short dissemination activity plan from each partner to be gathered as one dissemination activity plan for the project.
4. The Next preventive meeting in 2nd of July has been discussed; short presentations from George (EMaTTech), Thanasis (OUC), Ruba (JUST) and Leena (UJ) have been requested to be presented during the meeting. These presentations are related to EU water programs (George), dissemination activities (Ruba), Master program (Thanasis), and preparation W.P. 1 (Leena).
5. Arrangement for the next meeting in September, Kavala-Greece has been discussed. George requested the names and information from each participant, meanwhile he has sent information about locations and hotels, he suggested sending a bus to gather most of arrived partner from airport depending on their arrival times. Further discussions about these arrangements were suggested to be in further details during next skype meeting in August.
6. George (EMaTTech) provides an update about the external advisory committee; everything has been finalized and the names of the committee members have been approved.
7. George (EMaTTech) informed that deliverable 1.1.2. Review Water Education Curricula of major Universities in EU Countries has been completed and sent to all partners. This deliverable was completed with joint effort of all the EU Universities (EMaTTech, OUC, UPM and VU).
8. At this point the meeting was adjourned.

**End.**

1. **Dissemination level**: **PU** = Public, **RE** = Restricted to a group of the specified Consortium, **PP** = Restricted to other program participants (including Commission Services), **CO**= Confidential, only for members of the Consortium (including the Commission Services) [↑](#footnote-ref-1)